## Sheet 1
Table 1
Date | Vaibhav (Agentic Flow) | Lavnika (Backend Modularization + Sentiment) | Gunu (Flutter UX & Analytics) | Nadeem (Flutter UX & Analytics)
Wed, May 28 | • Outline the Agentic Flow state machine for Whole Brain Debrief: list states (e.g., Prompt, UserResponse, CoachSuggestion, Feedback). • Research existing RAG/RASA integration points in the Python repo—locate where chat messages are exchanged. | • Analyze monolithic Spring Boot project; identify “Whole Brain Debrief” and “Goal Setting” components. • Draft module plan: define two new services (debrief-service, goal-service) with clear APIs. • Create a new Python script skeleton for sentiment analysis. | • Audit current Flutter “Today” screen: locate widget tree and identify places to inject analytics calls. • Sketch a card‐based “TodayFeed” UI in code comments or on paper, noting where Gunu will place “NextActionCard” and “MoodCheckInCard.” | • Review Flutter bottom navigation; sketch changes: rename “Vault” → “Progress,” add stub screens for “Get Coached” and “Progress.” • Draft wireframes for “Actions” and “Progress” screens (on paper or Figma). • Create screen_routes.dart with placeholders (TodayFeed, ActionsScreen, GetCoachedScreen, ProgressScreen).
Thu, May 29 | • Define the Agentic Flow transitions in Python pseudocode (e.g., if sentiment < 0 then state = CoachSuggestion). • Draft Python functions: get_next_prompt(state, user_response) and update_state(previous_state, sentiment_score). | • Extract “Whole Brain Debrief” into a new Spring Boot module: – Create Maven project debrief-service. – Define REST endpoint /api/v1/debrief/chat. • Begin JUnit tests for DebriefController and DebriefService. • In Python: implement analyze_sentiment(text) (use Hugging Face or NLTK). | • Create a new Dart file analytics_events.dart with stub methods (logScreenViewed(), logMoodSelection(), etc.). • In main.dart, replace the current “Today” widget with an empty TodayFeed() placeholder. • Add an analytics call in initState() of TodayFeed to logScreenViewed('today'). | • Scaffold ActionsScreen in Flutter: an empty ListView with a placeholder “Next Up: Whole Brain Debrief” header. • In bottomNavigationBar, update item 4 text/icon to “Progress.” • Create ProgressScreen Dart file with an empty Column.
Fri, May 30 | • Translate Agentic Flow pseudocode into real Python code inside the existing RAG/RASA integration directory. • Write unit tests for state transitions (e.g., given a mock chat history, assert correct next prompt). • Document the Agentic Flow algorithm in a Markdown file. | • Extract “Goal Setting” into goal-service: – New Maven project, define /api/v1/goals. – Configure both services to depend on a shared “core-config” library (DB, security). • Write integration tests to confirm both modules start correctly. • In Python: extend sentiment script to read “Vaibhav” chat logs from DB. | • Implement TodayFeed widget: add a NextActionCard (hardcoded text “Whole Brain Debrief”). • Add a MoodCheckInCard below it; when tapped, show a modal with emojis. On emoji selection, call analytics.logMoodSelection(mood). • Instrument “21-day challenge” card to call analytics.logFeatureViewed('21_day_challenge') on render. | • In ActionsScreen, replace placeholder with a FutureBuilder calling fetchPendingActions() (returns hardcoded list of two actions). • Add a sticky “Next Up” header at top of the ListView. • In GetCoachedScreen stub, add a button “Chat with Sherlock” (empty for now). • In ProgressScreen, add a WiseCoinsCard with “0” (placeholder).
Mon, Jun 2 | • Integrate sentiment analysis into Agentic Flow: call analyze_sentiment(user_text) inside update_state() and adjust transitions accordingly. • Create an Agentic Flow API endpoint in Python (e.g., POST /agentic/next) that accepts chat_history and returns { next_prompt, new_state }. • Write end‐to‐end tests: feed a sample chat log, verify correct Agentic Flow output. | • Refactor shared JPA entities (DebriefRecord, GoalRecord) into a shared-model library. • Update both services to depend on shared-model. • Write JPA tests for shared entities. • In Python: schedule a daily job (e.g., via cron or a basic loop) that loads new “Whole Brain Debrief” chats, runs analyze_sentiment(), and writes to debrief_analysis(user, date, sentiment_score). | • Wire NextActionCard to a local Dart model: create ActionService.getNextAction() that returns NextAction(title: "Whole Brain Debrief", id: 1). • In MoodCheckInCard, after logging via analytics.logMoodSelection, also store the selected mood in a local state variable. • Update ActionsScreen so tapping an ActionItemCard logs analytics.logActionTapped(actionId) before doing nothing (stub). | • In ProgressScreen, replace placeholder with a ProgressChartPlaceholder (empty Container). • In GetCoachedScreen, wire “Chat with Sherlock” button to navigate to a new DebriefChatScreen. • Create DebriefChatScreen stub: an empty Column with a TextField at the bottom. • In ActionsScreen, add onTap to each action card that navigates to its detail (e.g., “GoalSettingScreen”).
Tue, Jun 3 | • Expose a new REST endpoint in Python: GET /analytics/debrief/vaibhav that returns the last 7 days’ { date, sentiment_score, agentic_state } from debrief_analysis. • Write a small README: how Agentic Flow works, how to call /agentic/next, and expected JSON schemas. • Begin integrating /agentic/next calls into the Spring Boot debrief-service—add a service class that calls the Python API. | • Write OpenAPI/Swagger docs for debrief-service and goal-service (use springdoc-openapi). • Add health checks (/actuator/health) to both services. • Set up GitHub Actions to build + push Docker images for each module to AWS ECR (staging). • In Python: ensure that analyze_sentiment() runs on any new “Vaibhav” chat (hooked into a simple loop). | • In TodayFeed, replace hardcoded NextActionCard with data from ActionService.getNextAction(). • Add a “Chat” button inside TodayFeed that navigates to DebriefChatScreen. • In DebriefChatScreen stub, log analytics.logChatScreenOpened() in initState(). • Start building chat UI: display a ListView of hardcoded messages (one “User: Hi” and one “Bot: Hello”). | • In ProgressScreen, add a “View Sentiment Trend” button. When tapped, call Lavnika’s /analytics/debrief/vaibhav endpoint (hardcoded URL) and display returned JSON as a vertical list (ListView.builder). • In GetCoachedScreen, add a “Saved Chats” section showing three dummy chat titles (ListTile). • In ActionsScreen, adjust styling: give the “Next Up” header a distinct background color.
Wed, Jun 4 | • Collaborate with Lavnika to finalize how /debrief-service calls the Python /agentic/next endpoint. • Write Spring Boot service method AgenticFlowClient.getNext(chatHistory) that sends a POST to the Python API and returns { prompt, state }. • Unit‐test AgenticFlowClient by mocking the Python service. | • Deploy both Spring Boot services (debrief-service, goal-service) to AWS staging (ECS/EKS). • Verify that /api/v1/debrief/chat is reachable. • In Python: integrate Agentic Flow into the sentiment job so that after computing sentiment, you also call update_state() and store agentic_state alongside sentiment_score in debrief_analysis. • Add JUnit/RestAssured tests for /analytics/debrief/vaibhav. | • In DebriefChatScreen, replace hardcoded messages with a StreamBuilder that listens to a local ChatService stream (initially empty). • Add a TextField + send button at the bottom; when “Send” is tapped, call analytics.logChatMessageSent(), append the user message to the stream, and display a placeholder “Bot is typing…” bubble. • In ActionsScreen, wire “GoalSettingScreen” navigation to a stub screen (empty page with “Coming Soon”). | • In ProgressScreen, replace the JSON list with a basic bar chart using charts_flutter (x-axis = date, y-axis = sentiment_score). • Style WiseCoinsCard to show a circle avatar + coin count from a stubbed UserService.getWiseCoins() (returns 10). • In GetCoachedScreen, wire “Saved Chats” list so that tapping one opens DebriefChatScreen with prefilled dummy history (hardcoded).
Thu, Jun 5 | • Finalize end‐to‐end flow: when /api/v1/debrief/chat receives a user message, the sequence is: 1. Save message to DB. 2. Call Python /agentic/next with updated chat history. 3. Receive { prompt, state }, save state to DB. 4. Return prompt back to Flutter. • Write integration tests covering this entire flow (Spring Boot → Python → DB → response). | • Merge module branches into main; tag releases (v1.0-debrief, v1.0-goal). • Coordinate with DevOps to push Docker images to production over the weekend. • Document “How to add a new bot” (e.g., Stress Management), including updating shared models and OpenAPI. • In Python, finalize nightly job (e.g., convert to cron job or AWS Lambda) that populates debrief_analysis with both sentiment and Agentic Flow states. | • In DebriefChatScreen, hook the “Send” button to call debrief-service: POST /api/v1/debrief/chat { user: “Vaibhav”, message: <text> } Then parse the JSON response { prompt, state } and append a “Bot: ” message to the stream. • Log each bot response via analytics.logBotMessageReceived(). • In ActionsScreen, add an “onLongPress” handler to each ActionItemCard that logs analytics.logActionLongPressed(actionId). | • In ProgressScreen, animate the bar chart so that each bar “grows” from 0 → sentiment_score when the screen loads. • Add a “Refresh” icon in the AppBar of ProgressScreen that re‐fetches /analytics/debrief/vaibhav and rebuilds the chart. • In GetCoachedScreen, add a “Start New Debrief” button that clears chat history in DebriefChatScreen and logs analytics.logNewChatStarted().
Fri, Jun 6 | • Oversee production rollout: verify that in production, /api/v1/debrief/chat correctly returns Agentic Flow prompts for live “Vaibhav” chats. • Monitor logs in CloudWatch for Python service—ensure Agentic Flow errors are < 1% of requests. • Finalize and share “Agentic Flow Handover” doc: explain how to tweak transitions, add new states, and interpret state codes. | • Monitor production Spring Boot services: ensure health checks remain green. • Run smoke tests on both services (via Postman or Newman). • Archive feature branches, update main README with module URLs, and update OpenAPI docs to point to production host. • Provide a “Backend Handover” PDF that includes DB schemas, key endpoints, and instructions for new bot integration. | • In DebriefChatScreen, style the chat bubbles: user messages on the right, bot messages on the left, each with a background color. • Add a small typing‐indicator animation (e.g., three dots) for the bot for 500 ms before displaying each response. • In ActionsScreen, add a pull‐to‐refresh that re‐reads assets/sample_actions.json. • In ProgressScreen, add a tooltip to each bar that shows “Date: , Score: ” on long‐press. | • Conduct a full QA pass on all updated screens (TodayFeed, Actions, GetCoached, Progress, DebriefChat, GoalSetting). • Write a “UX Handoff” document that details design decisions: card hierarchy, color palette, navigation logic, and future recommendations (e.g., gamification improvements). • Record a short demo video (screen capture) showcasing each screen’s functionality and analytics logs (e.g., show a console/Logcat printout of events).
Mon, Jun 9 | • Review first weekend’s production metrics: – Number of /debrief/chat calls – Average response time – Agentic Flow accuracy (manually spot‐check 10 chats). • Triage any urgent bugs (e.g., mismatched state transitions or missing prompts). • Plan a small feature: allow coaches to “override” Agentic Flow; document required API changes. | • Review production usage metrics: – Number of /analytics/debrief/vaibhav calls – Size of debrief_analysis table – Any errors in daily sentiment job. • Fix any issues in the nightly Python job (e.g., failed sentiment runs). • Update Python sentiment thresholds if initial results show noise (e.g., adjust negative/positive cutoff). | • In GetCoachedScreen, replace dummy “Saved Chats” with real data: call /analytics/debrief/vaibhav and show chat dates (use state from Agentic Flow as a badge). • Add deep linking: if the app is opened via a push notification “New Debrief Prompt,” navigate directly to DebriefChatScreen. • In ActionsScreen, add a “Mark All as Completed” button that logs analytics.logAllActionsCompleted(). | • In ProgressScreen, add a mini “Achievements” section below the bar chart: show three colored badge icons if wiseCoins >= 10; otherwise grayscale. • In DebriefChatScreen, add scrolling to bottom whenever a new message arrives. • In GoalSettingScreen, add a form with two TextFields (“Goal Title,” “Goal Description”) and a “Save” button; on save, log analytics.logGoalSaved().
Tue, Jun 10 | • Finalize “Agentic Flow v1.1” improvements based on weekend data: – If state transitions seem too aggressive, adjust transition rules. – Write a short “Agentic Flow Results” summary: examples of 5 chats and their state sequences. • Archive Python feature branch, tag release v1.0-agentic. • Deliver a final “Agentic Flow” slide deck for stakeholders: overview, metrics, next steps. | • Archive all feature branches for debrief-service and goal-service. • Update production OpenAPI docs to reflect final URLs and schemas. • Write a “Backend Post‐Mortem”: lessons learned, potential improvements (e.g., move sentiment/Agentic Flow into a Lambda for scalability). | • Conduct a final wrap‐up of Flutter analytics: verify that every analytics_events.dart call is firing (use a debug logger). • Replace any remaining hardcoded stubs (e.g., action lists) with final JSON assets or real endpoints. • Perform one last pass on all screens for consistency (fonts, padding, colors). | • Complete a final QA pass on GoalSettingScreen: ensure the form saves goals to a local stub service and logs analytics.logGoalSaved(). • Conduct an accessibility check: verify tappable areas ≥ 44×44 dp, color contrast ≥ 4.5:1. • Compile all UX docs, wireframes, and demo recordings into a single “UX Final Package” (PDF + video).
Date | Vaibhav (Agentic Flow) | Lavnika (Backend Modularization + Sentiment) | Gunu (Flutter UX & Analytics) | Nadeem (Flutter UX & Analytics)
Wed, May 28 | • Outline the Agentic Flow state machine for Whole Brain Debrief: list states (e.g., Prompt, UserResponse, CoachSuggestion, Feedback). • Research existing RAG/RASA integration points in the Python repo—locate where chat messages are exchanged. | • Analyze monolithic Spring Boot project; identify “Whole Brain Debrief” and “Goal Setting” components. • Draft module plan: define two new services (debrief-service, goal-service) with clear APIs. • Create a new Python script skeleton for sentiment analysis. | • Audit current Flutter “Today” screen: locate widget tree and identify places to inject analytics calls. • Sketch a card‐based “TodayFeed” UI in code comments or on paper, noting where Gunu will place “NextActionCard” and “MoodCheckInCard.” | • Review Flutter bottom navigation; sketch changes: rename “Vault” → “Progress,” add stub screens for “Get Coached” and “Progress.” • Draft wireframes for “Actions” and “Progress” screens (on paper or Figma). • Create screen_routes.dart with placeholders (TodayFeed, ActionsScreen, GetCoachedScreen, ProgressScreen).
Thu, May 29 | • Define the Agentic Flow transitions in Python pseudocode (e.g., if sentiment < 0 then state = CoachSuggestion). • Draft Python functions: get_next_prompt(state, user_response) and update_state(previous_state, sentiment_score). | • Extract “Whole Brain Debrief” into a new Spring Boot module: – Create Maven project debrief-service. – Define REST endpoint /api/v1/debrief/chat. • Begin JUnit tests for DebriefController and DebriefService. • In Python: implement analyze_sentiment(text) (use Hugging Face or NLTK). | • Create a new Dart file analytics_events.dart with stub methods (logScreenViewed(), logMoodSelection(), etc.). • In main.dart, replace the current “Today” widget with an empty TodayFeed() placeholder. • Add an analytics call in initState() of TodayFeed to logScreenViewed('today'). | • Scaffold ActionsScreen in Flutter: an empty ListView with a placeholder “Next Up: Whole Brain Debrief” header. • In bottomNavigationBar, update item 4 text/icon to “Progress.” • Create ProgressScreen Dart file with an empty Column.
Fri, May 30 | • Translate Agentic Flow pseudocode into real Python code inside the existing RAG/RASA integration directory. • Write unit tests for state transitions (e.g., given a mock chat history, assert correct next prompt). • Document the Agentic Flow algorithm in a Markdown file. | • Extract “Goal Setting” into goal-service: – New Maven project, define /api/v1/goals. – Configure both services to depend on a shared “core-config” library (DB, security). • Write integration tests to confirm both modules start correctly. • In Python: extend sentiment script to read “Vaibhav” chat logs from DB. | • Implement TodayFeed widget: add a NextActionCard (hardcoded text “Whole Brain Debrief”). • Add a MoodCheckInCard below it; when tapped, show a modal with emojis. On emoji selection, call analytics.logMoodSelection(mood). • Instrument “21-day challenge” card to call analytics.logFeatureViewed('21_day_challenge') on render. | • In ActionsScreen, replace placeholder with a FutureBuilder calling fetchPendingActions() (returns hardcoded list of two actions). • Add a sticky “Next Up” header at top of the ListView. • In GetCoachedScreen stub, add a button “Chat with Sherlock” (empty for now). • In ProgressScreen, add a WiseCoinsCard with “0” (placeholder).
Mon, Jun 2 | • Integrate sentiment analysis into Agentic Flow: call analyze_sentiment(user_text) inside update_state() and adjust transitions accordingly. • Create an Agentic Flow API endpoint in Python (e.g., POST /agentic/next) that accepts chat_history and returns { next_prompt, new_state }. • Write end‐to‐end tests: feed a sample chat log, verify correct Agentic Flow output. | • Refactor shared JPA entities (DebriefRecord, GoalRecord) into a shared-model library. • Update both services to depend on shared-model. • Write JPA tests for shared entities. • In Python: schedule a daily job (e.g., via cron or a basic loop) that loads new “Whole Brain Debrief” chats, runs analyze_sentiment(), and writes to debrief_analysis(user, date, sentiment_score). | • Wire NextActionCard to a local Dart model: create ActionService.getNextAction() that returns NextAction(title: "Whole Brain Debrief", id: 1). • In MoodCheckInCard, after logging via analytics.logMoodSelection, also store the selected mood in a local state variable. • Update ActionsScreen so tapping an ActionItemCard logs analytics.logActionTapped(actionId) before doing nothing (stub). | • In ProgressScreen, replace placeholder with a ProgressChartPlaceholder (empty Container). • In GetCoachedScreen, wire “Chat with Sherlock” button to navigate to a new DebriefChatScreen. • Create DebriefChatScreen stub: an empty Column with a TextField at the bottom. • In ActionsScreen, add onTap to each action card that navigates to its detail (e.g., “GoalSettingScreen”).
Tue, Jun 3 | • Expose a new REST endpoint in Python: GET /analytics/debrief/vaibhav that returns the last 7 days’ { date, sentiment_score, agentic_state } from debrief_analysis. • Write a small README: how Agentic Flow works, how to call /agentic/next, and expected JSON schemas. • Begin integrating /agentic/next calls into the Spring Boot debrief-service—add a service class that calls the Python API. | • Write OpenAPI/Swagger docs for debrief-service and goal-service (use springdoc-openapi). • Add health checks (/actuator/health) to both services. • Set up GitHub Actions to build + push Docker images for each module to AWS ECR (staging). • In Python: ensure that analyze_sentiment() runs on any new “Vaibhav” chat (hooked into a simple loop). | • In TodayFeed, replace hardcoded NextActionCard with data from ActionService.getNextAction(). • Add a “Chat” button inside TodayFeed that navigates to DebriefChatScreen. • In DebriefChatScreen stub, log analytics.logChatScreenOpened() in initState(). • Start building chat UI: display a ListView of hardcoded messages (one “User: Hi” and one “Bot: Hello”). | • In ProgressScreen, add a “View Sentiment Trend” button. When tapped, call Lavnika’s /analytics/debrief/vaibhav endpoint (hardcoded URL) and display returned JSON as a vertical list (ListView.builder). • In GetCoachedScreen, add a “Saved Chats” section showing three dummy chat titles (ListTile). • In ActionsScreen, adjust styling: give the “Next Up” header a distinct background color.
Wed, Jun 4 | • Collaborate with Lavnika to finalize how /debrief-service calls the Python /agentic/next endpoint. • Write Spring Boot service method AgenticFlowClient.getNext(chatHistory) that sends a POST to the Python API and returns { prompt, state }. • Unit‐test AgenticFlowClient by mocking the Python service. | • Deploy both Spring Boot services (debrief-service, goal-service) to AWS staging (ECS/EKS). • Verify that /api/v1/debrief/chat is reachable. • In Python: integrate Agentic Flow into the sentiment job so that after computing sentiment, you also call update_state() and store agentic_state alongside sentiment_score in debrief_analysis. • Add JUnit/RestAssured tests for /analytics/debrief/vaibhav. | • In DebriefChatScreen, replace hardcoded messages with a StreamBuilder that listens to a local ChatService stream (initially empty). • Add a TextField + send button at the bottom; when “Send” is tapped, call analytics.logChatMessageSent(), append the user message to the stream, and display a placeholder “Bot is typing…” bubble. • In ActionsScreen, wire “GoalSettingScreen” navigation to a stub screen (empty page with “Coming Soon”). | • In ProgressScreen, replace the JSON list with a basic bar chart using charts_flutter (x-axis = date, y-axis = sentiment_score). • Style WiseCoinsCard to show a circle avatar + coin count from a stubbed UserService.getWiseCoins() (returns 10). • In GetCoachedScreen, wire “Saved Chats” list so that tapping one opens DebriefChatScreen with prefilled dummy history (hardcoded).
Thu, Jun 5 | • Finalize end‐to‐end flow: when /api/v1/debrief/chat receives a user message, the sequence is: 1. Save message to DB. 2. Call Python /agentic/next with updated chat history. 3. Receive { prompt, state }, save state to DB. 4. Return prompt back to Flutter. • Write integration tests covering this entire flow (Spring Boot → Python → DB → response). | • Merge module branches into main; tag releases (v1.0-debrief, v1.0-goal). • Coordinate with DevOps to push Docker images to production over the weekend. • Document “How to add a new bot” (e.g., Stress Management), including updating shared models and OpenAPI. • In Python, finalize nightly job (e.g., convert to cron job or AWS Lambda) that populates debrief_analysis with both sentiment and Agentic Flow states. | • In DebriefChatScreen, hook the “Send” button to call debrief-service: POST /api/v1/debrief/chat { user: “Vaibhav”, message: <text> } Then parse the JSON response { prompt, state } and append a “Bot: ” message to the stream. • Log each bot response via analytics.logBotMessageReceived(). • In ActionsScreen, add an “onLongPress” handler to each ActionItemCard that logs analytics.logActionLongPressed(actionId). | • In ProgressScreen, animate the bar chart so that each bar “grows” from 0 → sentiment_score when the screen loads. • Add a “Refresh” icon in the AppBar of ProgressScreen that re‐fetches /analytics/debrief/vaibhav and rebuilds the chart. • In GetCoachedScreen, add a “Start New Debrief” button that clears chat history in DebriefChatScreen and logs analytics.logNewChatStarted().
Fri, Jun 6 | • Oversee production rollout: verify that in production, /api/v1/debrief/chat correctly returns Agentic Flow prompts for live “Vaibhav” chats. • Monitor logs in CloudWatch for Python service—ensure Agentic Flow errors are < 1% of requests. • Finalize and share “Agentic Flow Handover” doc: explain how to tweak transitions, add new states, and interpret state codes. | • Monitor production Spring Boot services: ensure health checks remain green. • Run smoke tests on both services (via Postman or Newman). • Archive feature branches, update main README with module URLs, and update OpenAPI docs to point to production host. • Provide a “Backend Handover” PDF that includes DB schemas, key endpoints, and instructions for new bot integration. | • In DebriefChatScreen, style the chat bubbles: user messages on the right, bot messages on the left, each with a background color. • Add a small typing‐indicator animation (e.g., three dots) for the bot for 500 ms before displaying each response. • In ActionsScreen, add a pull‐to‐refresh that re‐reads assets/sample_actions.json. • In ProgressScreen, add a tooltip to each bar that shows “Date: , Score: ” on long‐press. | • Conduct a full QA pass on all updated screens (TodayFeed, Actions, GetCoached, Progress, DebriefChat, GoalSetting). • Write a “UX Handoff” document that details design decisions: card hierarchy, color palette, navigation logic, and future recommendations (e.g., gamification improvements). • Record a short demo video (screen capture) showcasing each screen’s functionality and analytics logs (e.g., show a console/Logcat printout of events).
Mon, Jun 9 | • Review first weekend’s production metrics: – Number of /debrief/chat calls – Average response time – Agentic Flow accuracy (manually spot‐check 10 chats). • Triage any urgent bugs (e.g., mismatched state transitions or missing prompts). • Plan a small feature: allow coaches to “override” Agentic Flow; document required API changes. | • Review production usage metrics: – Number of /analytics/debrief/vaibhav calls – Size of debrief_analysis table – Any errors in daily sentiment job. • Fix any issues in the nightly Python job (e.g., failed sentiment runs). • Update Python sentiment thresholds if initial results show noise (e.g., adjust negative/positive cutoff). | • In GetCoachedScreen, replace dummy “Saved Chats” with real data: call /analytics/debrief/vaibhav and show chat dates (use state from Agentic Flow as a badge). • Add deep linking: if the app is opened via a push notification “New Debrief Prompt,” navigate directly to DebriefChatScreen. • In ActionsScreen, add a “Mark All as Completed” button that logs analytics.logAllActionsCompleted(). | • In ProgressScreen, add a mini “Achievements” section below the bar chart: show three colored badge icons if wiseCoins >= 10; otherwise grayscale. • In DebriefChatScreen, add scrolling to bottom whenever a new message arrives. • In GoalSettingScreen, add a form with two TextFields (“Goal Title,” “Goal Description”) and a “Save” button; on save, log analytics.logGoalSaved().
Tue, Jun 10 | • Finalize “Agentic Flow v1.1” improvements based on weekend data: – If state transitions seem too aggressive, adjust transition rules. – Write a short “Agentic Flow Results” summary: examples of 5 chats and their state sequences. • Archive Python feature branch, tag release v1.0-agentic. • Deliver a final “Agentic Flow” slide deck for stakeholders: overview, metrics, next steps. | • Archive all feature branches for debrief-service and goal-service. • Update production OpenAPI docs to reflect final URLs and schemas. • Write a “Backend Post‐Mortem”: lessons learned, potential improvements (e.g., move sentiment/Agentic Flow into a Lambda for scalability). | • Conduct a final wrap‐up of Flutter analytics: verify that every analytics_events.dart call is firing (use a debug logger). • Replace any remaining hardcoded stubs (e.g., action lists) with final JSON assets or real endpoints. • Perform one last pass on all screens for consistency (fonts, padding, colors). | • Complete a final QA pass on GoalSettingScreen: ensure the form saves goals to a local stub service and logs analytics.logGoalSaved(). • Conduct an accessibility check: verify tappable areas ≥ 44×44 dp, color contrast ≥ 4.5:1. • Compile all UX docs, wireframes, and demo recordings into a single “UX Final Package” (PDF + video).