## Sheet1
S.No. | Task | Details | Primary Owner | Dev Owner | Date | Source | KT Recording Link | Status | Gajendra Comment
1 | Application Context | Application Walkthrough - coaching app | Offline Recording | Aastha | 2024-11-25 | https://recalibratepvtltd.sharepoint.com/sites/Sherlock-TheWholeBrainSuperCoachBot/_layouts/15/stream.aspx?id=%2Fsites%2FSherlock%2DTheWholeBrainSuperCoachBot%2FShared%20Documents%2FGeneral%2FRamp%20Up%2FRamp%20Recordings%2FRamp%20up%2D%20Sherlock%20App%2Emp4&referrer=Teams%2ETEAMS%2DELECTRON&referrerScenario=teamsSdk%2DopenFilePreview |  |  | Link not working. Romila to update
2 | Technical Oversight | Overall application architecture, One Note, Design Diagrams, Components | Gajendra |  | 2024-11-25
3 | Technical Context | High level components - CMS | Offline Recording | Satyam | 2024-11-26 |  | CMS-20240821_174603-Meeting Recording.mp4
4 | Technical Context | High level components - Backend | Offline Recording | Lavnika | 2024-11-26 |  | Ramp Up - Backend -20240822_100438-Meeting Recording.mp4
5 | Technical Context | High level components - UI | Offline Recording | Ubaid | 2024-11-27 |  | Ramp Up Of UI-20240827_093628-Meeting Recording.mp4
6 | Technical Context | High level components - Bot | Satyam | Satyam | 2024-11-27 |  |  |  | Romila to provide updated link
7 | Technical Context | Dev Setup (UI, Backend, STRAPI, Bot) | Offline Activity | Satyam, Lavnika, Ubiad | 2024-11-27 | Multi days activity.
8 | Technical Context | Important APIs and integrations(includes Backend API integration in Strapi) | Offline Recording | Lavnika | 2024-11-28 | https://recalibratepvtltd.sharepoint.com/:v:/s/Sherlock-TheWholeBrainSuperCoachBot/Eab-iPrAY79GtbN3BxapX40B4ZQeHPy0DbfIbluY6oQSWA?e=NKQ9or | Ramp Up - Api Integration and Data Model-20240823_100724-Meeting Recording.mp4 |  | Link not working. Romila to update
9 | Technical Context | Deployment Architecture, Jenkins and CI/CD pipeline, Build and Deployment process | Offline Recording | Lavnika | 2024-11-28 |  | Ramp Up - Ci Cid -20240822_120136-Meeting Recording.mp4
10 | Technical Oversight | SOC 2 Control and related policy Transition | Gajendra |  | 2024-11-28
11 | Technical Oversight | Code Reviews, Playbook Review Sign off, Tech Debt Prioritization, MongoDB production access, Access (AWS, Mongo, Firebase, Apple, Google Playstudio, Github, OpenAI) | Gajendra |  | 2024-11-29
12 | Technical Context | LLM Integration: Langchain, Azure, Gemini, Bedrock LLM Custom EVALs | Gajendra | Satyam | 2024-11-29
13 | Technical Oversight | Cost Analysis & Optimization AWS, MongoDB, Azure, OpenAI, GitHUB | Gajendra |  | 2024-12-02
14 | Technical Context | Application Security (Guard Duty, Patch management, WAF, private subnets, authentication/authorization/entitlement) | Gajendra |  | 2024-12-02
15 | Technical Context | Streaming Design component and thought process | Gajendra | Satyam | 2024-12-03
16 | Technical Context | RAG Design Components and Though Process | Gajendra | Shaddam/Satyam | 2024-12-03
17 | Technical Context | Voice Design and Web Voice implementation | Gajendra | Satyam | 2024-12-04
18 | Technical Context | Training ML Models for tools | Gajendra |  | 2024-12-05
19 | Technical Context | Observability (Grafana, Prometheus, Xray) | Lavnika | Lavnika/Bibek | 2024-12-05
20 | Technical Context | Observability follow up conversation with Gajendra | Gajendra | Lavnika/Bibek | 2024-12-06
21 | Technical Context | Infra Common (Gajendra managed code) | Gajendra |  | 2024-12-09
22 | Technical Context | Fine Tuning of Whole Brain Model | Gajendra |  | 2024-12-10
23 | Acumen Application Context | Application Walkthrough | Offline Recording | Bibek | 2024-12-10 | Romila to share recordings
24 | Acumen Technical Context | Migration, Engagement, Effectiveness, AI Summary … | Bibek/Gunu | Bibek | 2024-12-11
25 | Technical Context | Static Website, Certificate Installation | Gajendra | Shaddam | 2024-12-12 | Shaddam is not aware of certificate installation
26 | Technical Oversight | Private Keys and Credentials Information handover | Gajendra |  | 2024-12-13
27 | General Processes | Project Management Processes i. JIRA ii. Scrums Team Structure | Romila |  | 2024-12-13
28 | Technical Oversight | Team Information | Gajendra |  | 2024-12-13 | Include Romila